## Slide 1: Balboa Islands Seawall Rehabilitation Project

## Slide 2: Two primary Issues
1) Need to address the structural condition of the aging seawalls.
2) Need to consider sea level rise when setting a top elevation of the new wall or cap.

## Slide 3: Table of Contents
Overview
Existing Conditions
Overtopping concerns (Sea Level Rise)
    Flood Potential
    Minimum Top of Wall Elevation
Seawall Replacement, Rehabilitation or Raised Cap
Costs
    Jetty Tide Gate
    Beach and Dock Access
Other Considerations
    Ferry Landing
    Storm Drain Collection System

## Slide 4: Newport Harbor Overview

## Slide 5: Low-Lying Areas Around the Harbor

## Slide 6: Public and Private Bulkheads and Seawalls (fix exhibit)

## Slide 7: City-Owned Seawalls

## Slide 8: Project Site Overview
West
End

## Slide 9: Grand Canal

## Slide 10: Grand Canal

## Slide 11: Grand Canal

## Slide 12: Little Balboa Island

## Slide 13: Balboa Island – West End

## Slide 14: Balboa Island – Typical Floating Dock

## Slide 15: Collins Island (Private)

## Slide 16: Historic Ferry Boat Landing

## Slide 17: Residential Interface

## Slide 18: Existing Conditions

## Slide 19: As-Built Conditions

## Slide 20: Ballast placed at West End in 1985 - to Prevent Scour

## Slide 21: Pile Crack (West End)

## Slide 22: Pile Crack (Close-up)

## Slide 23: Wall Movement (West End)

## Slide 24: Condition Survey

## Slide 26: Balboa Islands Seawalls – Condition Summary
85 year old walls. (Original lifespan approximately 75 years. )
Walls are exhibiting obvious signs of deterioration and stress.
Existing walls subject to seismic risk.
Grand Canal: Depth of wall below mudline is very shallow.
Many unknowns: seawall rebar, sheetpile condition below mudline, tiebacks.
Useful lifetime: 10-25 years (2011 report)

## Slide 27: Flood Potential

## Slide 28: West End Balboa Island, King Tide, 12/12/2013

## Slide 29: Wave Overtopping During Storm Event

## Slide 30: Overtopping Due To Storm Surge

## Slide 31: City Emergency Response
Public Works staff mobilize emergency pump stations throughout the City.

## Slide 32: Flooding at Balboa Island Ferry Landing (2005)

## Slide 33
Sea Level Rise Predictions – 2100 The 95% column on the right side indicates that there is a 5% chance the predicted sea level rise will be exceeded.
Agency | Year | 5% | 50% | 95% (high confidence)
IPCC 4th Assessment | 2007 | 9” | 15” | 20”
Vermeer and Rahmstorf | 2009 | 39” | 49” | 61”
US Corps of Engineers | 2011 | 17” | 39” | 59”
National Academy of Sciences (& California Coastal Commission) | 2012 | 17” | 37” | 66”
IPCC 5th Assessment | 2013 | 17” | 24” | 31”
Quaternary Science Reviews | 2014 | 28” | 37” | 47”
California State Coastal Conservancy in 2009 adopts Climate Change Policy of 55-inch sea level rise by 2100.

## Slide 34: 2010 Flood Scenario 3: Ocean Swell

## Slide 35: December 2010 Flooding on Turquoise - Extreme Tide p=40% w/ Ocean Swell

## Slide 36: Existing Seawall, Year 2025, 1% Tide, Wind Waves

## Slide 37: Wind Waves at High Tide

## Slide 38: Existing Seawall, Year 2050, 10% Tide, No Waves

## Slide 39: Extreme Tide Height Projections

## Slide 40: Seawall Replacement and Rehabilitation

## Slide 41: Proposed New Seawall Concept
Elevation Datum: NAVD88

## Slide 42: Increase Top of Wall Elevation  Provides flood protection until 2025
LOCATION Now New Difference
Balboa Island N. 7.8’ 8.5’ +8.4 inches
Balboa Island S. 8.25’ 9.0’ +9 inches
Grand Canal 8.5’ 8.5’
Little Island E. 8.7’ 8.7’
Little Island S. 9.0’ 9.0’
* all elevations based on NAVD88 datum.

## Slide 43: Steel Sheet Piles (Silent Pile Driver)

## Slide 44: Bay Island: Steel Sheet Piles and Cap

## Slide 45: Bay Island Sheet Piles and Cap

## Slide 46: Similar Installation - Naples Island, Long Beach, CA

## Slide 47: Projected Cost – Option A
Rehabilitation Option | Seawall Useful Lifetime | Initial Cost
Option A: All New Seawalls | 100 years | $70 million
Notes:
25% Contingency
Cantilevered wall designed to take extension up to Elevation 14.0.
Costs includes seawalls, caps, pier and beach access ramps, modifications to entrances at Historic Ferry Landing and Collins Islands, and ADA modifications to the boardwalk near Mariner’s Bridge.
Seawall costs are based on 2014 bids for new seawalls for Naples Island, Long Beach.
Costs shown in today’s dollars.
Elevation Datum: NAVD88

## Slide 48: Option B: new Seawalls at West End and Grand Canal. Cap the other walls.

## Slide 49
PROPOSED 9-INCH CAP EXTENSION

## Slide 50: Example: Little Balboa Seawall Cap Extension

## Slide 51: Projected Costs – Options A & B
Rehabilitation Option | Seawall Useful Lifetime | Initial Cost
Option A All New Seawalls (Initial Top Elevation: 10 feet) | 100 years Raise walls after ~2060 if needed | $70 million
Option B New Seawalls along West End and Grand Canal only Cap Remaining | 100 years 20-25 years then replace capped walls | $32million (> $45 million)

## Slide 52: Earth Anchor and Waler

## Slide 53: Earth Anchors at Balboa Island Ferry Landing

## Slide 54: Annual Sand Buttressing

## Slide 55: Projected Costs: Options A, B & C
Rehabilitation Option | Seawall Useful Lifetime | Initial Cost
Option A All New Seawalls | 100 years | $70 million
Option B New Seawalls along West End and Grand Canal only Cap Remaining | 100 years 20-25 years then replace capped walls | $32 million (>$45 million)
Option C New Seawall along Southwest End Earth Anchors at Northwest End & Grand Canal Cap Remaining | 100 years 20-25 years then replace with new seawalls | $17 million (>$55 million)

## Slide 56: Option D – Cap Extensions and seawall rehab only--- $14 million

## Slide 57: If sea levels rise about 4 feet, ocean side beaches will need to be raised.

## Slide 58: Jetty Gate Alternative

## Slide 59: Sea Level Rise Alternative Solution

## Slide 60: Conceptual Tide Gate

## Slide 61: Conceptual Tide Gate

## Slide 62: Conceptual Tide Gate

## Slide 63: Tidelands Committee – Recommendations for Future Consideration of Jetty Gate
Confirm magnitude and rate of sea level rise.
Install tide gauge in harbor.
If we truly are experiencing rapid sea level rise of 66 inches by 2100, we should be able to measure a ~2 inches of sea level rise by ~2020.
More expensive analysis can be found on City’s website.

## Slide 64: Other Considerations - Access

## Slide 65: Access onto Private Dock

## Slide 66: Access onto Private Dock

## Slide 67
Stepping Up and Over onto Private Dock

## Slide 68
3-Foot Wide Gaps in Seawall Cap for Beach Access

## Slide 69: Other Items under Consideration
Flooding at Ferry Landing
Protection at Collins Island
Protection from Rising Groundwater
Raising Boardwalk
Funding

## Slide 70: Questions/Discussion